## Sheet4
NOTIONAL BUDGET - NOT A JPL ASSURED COST (rather, this is one engineer's rough model to enable early architecture formulation trades)
Does not constitute an implementation-cost commitment on the part of JPL or Caltech. The accuracy of the below is commensurate with the level of understanding of the mission concept, pre-TeamX, and pre-Phase A.
1000 | Mission cost including L/V [Note: this spreadsheet explores the hard-limiting case; strongly recommend proposing well below the cap to accommodate anticipated cost upper from ICE]
| 150 | Launch Vehicle (firm number given to us by NASA)
| 850 | Phase A-E Mission Costs with Reserves, w/o L/V
|  | 125 | Phase E-F cost+reserves (estimate based on EPIC-IM report inflated to $FY17, assuming 4yr of operations)
|  | 725 | Phase A-D Mission Costs with Reserves
|  |  | 215 | Phase A-D Reserves (from NASA briefing "Costing Rules of Thumb" slide)
|  |  | 510 | Phase A-D Mission Costs w/o Reserves
|  |  |  | 100 | Phase A-D Project Management, Project Systems Engineering, Mission Assurance, Science, Mission Operations, Ground Data Systems (from NASA briefing "Costing Rules of Thumb" slide)
|  |  |  | 410 | Observatory including AI&T [Note: with the exception of reducing years of operations, little can be done to reduce perceived costs above this line] [as NASA briefing says, "Non-hardware costs have limited potential for savings"]
[5 empty] | 30 | ATLO [Observatory Assembly, Test and Launch Operations] (estimate based on EPIC-IM report)
[5 empty] | 200 | Spacecraft including Management, Systems Engineering, Subcontractor Management, Subcontractor Systems Engineering, Subcontractor Mission Assurance, Power, Command & Data Handling, Telecom, Mechanical, Thermal, Propulsion, Attitude Determination & Control, Bus Harness, Flight Software (estimate based on modeling and parametric study of actuals by Team X leads based on estimated mass, power, data, etc. of payload) (Note: one notable requirement driving our spacecraft cost is relatively large payload power draw, needed for active cooling)
[5 empty] | 180 | Payload
[6 empty] | TBD | Payload Management, Systems Engineering, Integration & Test
[6 empty] | 60-90M? | Total Thermal System [not yet quantitatively studied, so we assume here that the spectrometer requirements for a 2.7K stage and for 100mK cooling will be cost-balanced by reduced cooling needs of a smaller imager relative to imager-only concept]
[7 empty] | 0 | (No deployed sunshield)
[7 empty] | 15 | Passive cooling (vgrooves) & thermal design & radiation shields (WAG cost)
[7 empty] | 45 | Active cooling to ~4-6K (EPIC-IM report 4K cooling costs inflated to $FY17)
[7 empty] | 30 | Active cooling from ~4-6K to ~100mK (EPIC-IM report ADR costs inflated to $FY17)
[6 empty] | 38-50M? | Spectrometer, w/o thermal/cryo
[7 empty] | 38 | CBE (50% cost) from Al Kogut, including Instrument Management, Instrument Systems Engineering, Assurance, Instrument I&T, Electronics, Optics, Detectors, Mechanisms, etc.
[7 empty] | TBD | Margin
[6 empty] | 40-80M? | Imager, w/o thermal/cryo
[7 empty] | ~25% | Imager Management, Systems Engineering, Integration & Test
[7 empty] | 30-60M? | Imager Hardware & Software (for scale, note this was ~150M for the EPIC-IM report "4K Option" concept scaled to $FY17)