## Slide 1: PICO I+T
Input to TeamX-M 03/2018

## Slide 2: Schedule and Tasks
Phase A (12 months): No I+T
Phase B (12 months):
    Device level detector testing [Foundries, University Labs]
Phase C (22 months):
  Phase C1 (10 months):
    Cooler qualification
    Telescope cryogenic photogrammetry
    Begin Focal plane (+ SubK cooler) I&T
  Phases C2 (12 months):
    Complete Telescope I&T (including environments)
    Complete Focal plane (+ SubK cooler) I&T
    Integration/alignment of Telescope + Focal Plane
Phase D (18 months)
  Phase D1 (14 months)
    Complete Instrument I&T (including environments)
    Observatory I&T
  Phase D2 (4 months)
    Launch Ops

## Slide 3: Device testing
Device level detector screening + characterization
  What: verify TC , RN , PSAT , yield, optical efficiency & spectral response
  Hardware: individual detector wafers
  Where: Foundries, University Labs
  When: following / in parallel with fabrication

## Slide 4: Subsystem testing
Cooler qualification
  What: verify 18, 4.5 K, and 0.1 K cooler performance
  Hardware: Kelvin and sub-K coolers
  Where: Subsystem testbeds + Industry
Telescope (reflectors and truss) cryogenic photogrammetry
  Hardware: primary and secondary reflectors
  Where: TVAC chamber (300-40 K)
  How long: ~1 month total; 2 cold runs 3 days each
Focal plane + SubK cooler I&T
  What:
    Integration of the flight cooler and full FPU (focal plane unit) + Cryogenic characterization
    Noise, responsivity, stability with representative optical load for each band
    Polarimetric calibration
    Spectroscopic calibration
  Hardware: Focal plane, Readout electronics, Sub-Kelvin cooler
  Where: dedicated, sub-K cryogenic testbed
  How long: 6 months total allocated to task; 3 cold runs, each 3 weeks.

## Slide 5: Instrument integration & testing
Integration/alignment of Telescope (reflectors) + Focal Plane
  What:
    Focal plane is fixed; secondary and primary aligned to focal plane.
    Mount reflectors in position at ambient temperature accounting for expected thermal contraction, verify with photogrammetry + interferometry
    Verify alignment at cold temperatures using photogrammetry + interferometry
  Hardware: Focal plane, Telescope
  Where: …
  How long: …
Instrument level testing/calibration
  What:
    Environmental testing
    Post-environments characterization
  Hardware: Focal plane, Readout electronics, Sub-Kelvin cooler, 4K cooler, Telescope
  Where: …
  How long: 4 months?

## Slide 6: Observatory-level performance testing
Observatory TVAC performance testing
  What: Constrain parasitic optical loading from the instrument, noise, microphonics, RFI (Telemetry, spacecraft bus)
  Hardware: spacecraft + instrument (cold + Vac)
  Where: environmental chamber
  How long: 2 months